## Critical Path Analysis
Step | Task | Length(days) | sequential or parallel | dependant on | Leader/assigned to | Set Due Dates | Mark x if done | LEGEND
Section 1 | [8 empty] | finished section
a | Initial Soldering | 2 |  | n/a | Miguel |  | x |  | overdue task
b | order duplicates | 2 | parallel | 1a | TEAM |  | x |  | partially finished section
total |  | 2 |  |  |  |  | x |  | in progress task
Section 2 | [8 empty] | future task
a | battery verification | 3 | sequential | 1a | Vance |  | x |  | future section
b | pin pad verification | 3 | parallel | 2a | Vance |  | x
c | limit switch verification | 3 | parallel | 2a | Vance |  | x
d | closer verification | 3 | parallel | 2a | Ash |  | x
total |  | 3 |  |  |  |  | x
Section 3
a | PIN Pad + Lock Subsystem verification | 2 | sequential | 2b | Vance |  | x
b | Alarm Subsystem verification | 2 | parallel | 3a | Vance |  | x
total |  | 2 |  |  |  |  | x
Section 4
a | 3d modeling case | 7 | parallel | 1a | Ash/Brayden |  | x
b | 3d modeling backplate | 7 | parallel | 4a | Ash/Brayden |  | x
total |  | 7 |  |  |  |  | x
Section 5
a | 3d printing case | 3 | sequential | 4a | Ash/Brayden |  | x
b | 3d print brackets | 3 | Parallel | 5a | Ash/Brayden |  | x
c | 3d printing backplate | 3 | parallel | 5a | Ash/Brayden |  | x
total |  | 3 |  |  |  |  | x
Section 6
a | Prototype Assembly | 4 | sequential | 5a | Miguel |  | x
total |  | 4 |  |  |  |  | x
Section 7
a | Full Assembly Functionality Test | 4 | sequential | 6a | TEAM |  | x
b | Battery Life Test | 4 | parallel | 7a | Miguel |  | x
c | Final Weight | 1 | parallel | 7a | Ash |  | x
total |  | 4 |  |  |  |  | x
Section 8
a | DR3 | 1 | sequential | 7a | TEAM | 2024-04-23 | x
total |  | 1 |  |  |  |  | x
Section 9
a | Revise Case Body Model | 7 | sequential | 8a | Ash/Brayden |  | X
b | Reprint Case | 3 | sequential | 9a | Brayden |  | x
c | Finalize Code | 4 | parallel | 9b | Vance
c1 | Look for possible ways to use circuit incorrectly | 2 | parallel | 9b | TEAM |  | x
c2 | Minimize/provide solutions to device misuse | 2 | sequential | 9c2 | TEAM
c3 | Replace testing values with usage values | 1 | parallel | 9c1 | Vance |  | x
d | Refinement/Troubleshooting | 4 | sequential | 9a | TEAM
d1 | Look for possible ways to improve physical device design | 2 | sequential | 9a | TEAM |  | x
d2 | Look for possible ways to misuse device | 2 | parallel | 9d1 | TEAM |  | x
d3 | Minimize/provide solutions to device misuse | 2 | sequential | 9d2 | TEAM
e | Progress Report 4 draft | 14 | parallel | 9a-9d | Miguel
total |  | 14
Section 10
a | Final Assembly | 14 | sequential | 9d | TEAM
b | Final Cost | 1 | parallel | 10a | Miguel |  | x
c | Showcase poster | 14 | parallel | 10a | Miguel | 2024-05-26 | x
total |  | 14
Section 11
a | Progress Report 4 | 14 | sequential | 10c | TEAM | 2024-06-03
total |  | 14
Section 12
a | design showcase | 1 | sequential | 11a | TEAM | 2024-06-06
total |  | 1
Sign | Date | Time
Vance Padilla | 2024-04-22 | 22:10
Ashwin Halepet
Miguel Cruz | 2024-04-22 | 21:59
Brayden Chipman | 2024-04-22 | 20:36