## Fall Quarter
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Task | 10/8-10/14 | 10/15-10/21 | 10/22-10/28 | 10/29-11/4 | 11/5-11/11 | 11/12-11/18 | 11/19-11/25 | 11/26-12/2 | 12/3-12/9 | 12/10-12/16
Problem Formulation
Creation of User Needs Survey | bar: Week 1
Contacting Users For Survey | bar: Week 2 to Week 3
Benchmarking | bar: Week 2
EDS (Measurements) | bar: Week 3
House of Quality | bar: Week 3
Progress Report 1 | bar: Week 3 to Week 4
Progress Report Slides | bar: Week 4
Design Review 1 | bar: Week 4
Meeting with Client
Development of User Needs Statement
CATME Peer Evaluation | bar: Week 5
Conceptual Design
Initial Prototpying | bar: Week 7 to Week 10
Concept Feasibility and Screening | bar: Week 6 to Week 8
Progress Report 2 | bar: Week 7 to Week 10
Sign | Week 1: Date; Week 2: Time
Vance Padilla | Week 1: 2023-11-15; Week 2: 19:35
Ashwin Halepet | Week 1: 2023-11-15; Week 2: 19:35
Miguel Cruz | Week 1: 2023-11-15; Week 2: 19:35
Brayden Chipman | Week 1: 2023-11-15; Week 2: 19:35

## Winter Quarter
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Task
Conceptual Design
Progress Report 2 | bar: Week 1 to Week 3
Design Review 2 | bar: Week 1 to Week 3
Materials and Manufacturing Screening | bar: Week 1 to Week 4
Verification/Validation | bar: Week 4 to Week 5
FMEA | bar: Week 6 to Week 7
Societal Impact | bar: Week 8 to Week 10
Progress Report 3 | bar: Week 4 to Week 10
Design Review 3 | bar: Week 4 to Week 10
Prototyping | bar: Week 4 to Week 10
Sign | Date | Time | Date | Time | Date | Time
Vance Padilla | 2024-01-23 | 22:54 | 2024-02-01 | 19:21 | 2024-03-07 | 19:37
Ashwin Halepet | 2024-01-23 | 10:18 | 2024-02-01 | 19:21 | 2024-03-08 | 16:18
Miguel Cruz | 2024-01-23 | 10:18 | 2024-02-01 | 19:21 | 2024-03-08 | 16:18
Brayden Chipman | 2024-01-23 | 10:18 | 2024-02-01 | 19:21 | 2024-03-07 | 19:37

## Spring Quarter
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Task | 3/31-4/6 | 4/7-4/13 | 4/14-4/20 | 4/21-4/27 | 4/28-5/4 | 5/5-5/11 | 5/12-5/18 | 5/19-5/25 | 5/26-6/1 | 6/2-6/8
Prototyping
Initial Soldering | bar: Week 1
Verification Tests | bar: Week 2 to Week 3
3D Modelling | bar: Week 2 to Week 3
3D Printing | bar: Week 2 to Week 3
Prototype Assembly | bar: Week 3 to Week 4
Validation Tests | bar: Week 3 to Week 4
Design Review 3 | bar: Week 4
Finalizing Design
Laser Cutting | bar: Week 5 to Week 7
Welding | bar: Week 5 to Week 7
Refinement | bar: Week 5 to Week 7
Progress Report 4 | bar: Week 6 to Week 9
Final Assembly | bar: Week 8 to Week 9
Design Showcase | bar: Week 10
Sign | Week 1: Date; Week 2: Time
Vance Padilla | Week 1: 2024-04-22
Ashwin Halepet
Miguel Cruz | Week 1: 2024-04-22; Week 2: 21:45
Brayden Chipman | Week 1: 2024-04-22; Week 2: 20:36

## Critical Path Analysis
Step | Task | Length(days) | sequential or parallel | dependant on | Leader/assigned to | Set Due Dates | Mark x if done | LEGEND
Section 1 | [8 empty] | finished section
a | Initial Soldering | 2 |  | n/a | Miguel |  | x |  | overdue task
b | order duplicates | 2 | parallel | 1a | TEAM |  | x |  | partially finished section
total |  | 2 |  |  |  |  | x |  | in progress task
Section 2 | [8 empty] | future task
a | battery verification | 3 | sequential | 1a | Vance |  |  |  | future section
b | pin pad verification | 3 | parallel | 2a | Vance |  | x
c | limit switch verification | 3 | parallel | 2a | Vance |  | x
d | closer verification | 3 | parallel | 2a | Ash |  | x
total |  | 3
Section 3
a | PIN Pad + Lock Subsystem verification | 2 | sequential | 2b | Vance |  | x
b | Alarm Subsystem verification | 2 | parallel | 3a | Vance |  | x
total |  | 2 |  |  |  |  | x
Section 4
a | 3d modeling case | 7 | parallel | 1a | Ash/Brayden |  | x
b | 3d modeling backplate | 7 | parallel | 4a | Ash/Brayden |  | x
total |  | 7 |  |  |  |  | x
Section 5
a | 3d printing case | 3 | sequential | 4a | Ash/Brayden |  | x
b | 3d print brackets | 3 | Parallel | 5a | Ash/Brayden |  | x
c | 3d printing backplate | 3 | parallel | 5a | Ash/Brayden |  | x
total |  | 3 |  |  |  |  | x
Section 6
a | Prototype Assembly | 4 | sequential | 5a | Miguel |  | x
total |  | 4 |  |  |  |  | x
Section 7
a | Full Assembly Functionality Test | 4 | sequential | 6a | TEAM |  | x
b | Battery Life Test | 4 | parallel | 7a | Vance
c | Final Weight | 1 | parallel | 7a | Ash
total |  | 4
Section 8
a | DR3 | 1 | sequential | 7a | TEAM | 2024-04-23 | x
total |  | 1 |  |  |  |  | x
Section 9
a | Revise Case Body Model | 7 | sequential | 8a | Ash/Brayden
b | Reprint Case | 3 | sequential | 9a | Brayden
c | Finalize Code | 3 | parallel | 9b | Vance
d | Refinement | 4 | sequential | 9a | TEAM
e | Progress Report 4 draft | 14 | parallel | 9a-9d | Miguel
total |  | 14
Section 10
a | Final Assembly | 14 | sequential | 9d | TEAM
b | Final Cost | 1 | parallel | 10a | TEAM
c | Showcase poster | 14 | parallel | 10a | Miguel | 2024-05-26
total |  | 14
Section 11
a | Progress Report 4 | 14 | sequential | 10c | TEAM | 2024-06-03
total |  | 14
Section 12
a | design showcase | 1 | sequential | 11a | TEAM | 2024-06-06
total |  | 1
Sign | Date | Time
Vance Padilla | 2024-04-22 | 22:10
Ashwin Halepet
Miguel Cruz | 2024-04-22 | 21:59
Brayden Chipman | 2024-04-22 | 20:36