## Fall Quarter
Task | 10/8-10/14 | 10/15-10/21 | 10/22-10/28 | 10/29-11/4 | 11/5-11/11 | 11/12-11/18 | 11/19-11/25 | 11/26-12/2 | 12/3-12/9 | 12/10-12/16 | 12/17-12/23
Team Meeting | 2 hour | 1 hr | 1 Hr | 1Hr | 0 Hr | 1 Hr | 1 Hr | 2 Hr
Client Meeting | 1 Hour | 1 hour
Weekly Deliverables | User Needs Survey | Benchmarking Table | EDS | Presentation |  | Concept feasibility and screening | Concept feasibility and screening | Concept feasibility and screening
MC | 50 min | 1.5 hr | 1 hr | 2Hr |  | 1hr | 2 Hr
BC | 1 Hr 20 min | 1 Hr | 1 hr | 2Hr |  | 1hr | 1 1/2 Hr |  |  | 1hr
VP | 1 Hr | 1 Hr | 1 hr | 1Hr
AH | 1 Hr |  |  | 2 hr |  |  |  |  | 2 Hr (CAD)
Research
MC
BC
VP
AH
TA Meeting | 1.5 hr | 30 min | 1Hr | 1Hr | 1Hr |  |  | 40 min | 6 min
Project Progress Report 1
MC |  | 2 hr | 3 hr
BC |  | 2 hr | 4 hr
VP |  | 1.5 hr | 2.5 hr
AH |  | 1.5 hr | 2.5 hr
Revisons | [5 empty] | User Needs Statement, DHF Organization, User Needs Survey
MC | [5 empty] | 1.5 hrs
BC | [5 empty] | 1.5 hrs
VP | [5 empty] | 1.5 hrs
AH | [5 empty] | 1.5 hrs

## Winter Quarter
Task | 12/31-1/6 (Christmas Break) | 1/7-1/13 | 1/14-1/20 | 1/21-1/27 | 1/28-2/3 | 2/4-2/10 | 2/11-2/17 | 2/18-2/24 | 2/25-3/2 | 3/3-3/9
Team Meeting |  | 1 Hr | 1 Hr | 4 Hr | 1 Hr | 1 Hr | 2 Hr | 2 Hr | 2 Hr | 3 Hr
Client Meeting |  |  |  |  | 1.5 Hr
Other Meetings
Steven Lucero |  | 45 min
Weekly Deliverables |  | Materials and Manufacturing Screening |  |  |  | Primary Testing Plan | Primary Testing Plan/FMEA | FMEA
MC |  | 1 Hr |  |  |  | 2 Hr | 2 Hr | 2 Hr
BC |  | 1 Hr |  |  |  | 2 Hr | 1.5 Hr | 1 Hr
VP |  | 1 Hr
AH |  | 1 Hr |  |  |  | 2 Hr | 1 Hr | 1 Hr
Research
MC |  | 30 min |  | 1 Hr |  |  |  |  | 30 min | 10 min
BC |  | 30 min | 15 min | 10 min |  |  | 1 Hr
VP |  |  | 1 Hr | 2 Hr | [5 empty] | 1Hr
AH |  |  | 2 Hr | 2 Hr | 1 Hr
TA Meeting |  | 15 min | 20 min | 45 min | 30 min | 40 min |  | 15 min | 30 min | 15 min
Project Progress Report 2 |  |  |  |  | Project Progress Report 3
MC | 1 Hr | 30 min | 3 hrs | 4 Hr | MC |  |  |  | 2 Hr | 5 Hr
BC | 1 Hr | 2 Hr | 1 Hr | 4 Hr | BC |  |  |  | 2 Hr | 5 Hr
VP | 2 Hr | 2 Hr | 1 Hr | 4 Hr | VP |  |  |  | 3 Hr | 4 Hr
AH | 30 min | 1 Hr | 2 Hr | 4 Hr | AH |  |  |  | 1 Hr | 2 Hr
Design Review 2 |  |  |  |  | Design Review 3
MC |  |  |  | 3 Hr
BC |  |  |  | 2 Hr
VP |  |  |  | 2 Hr
AH |  |  |  | 3 Hr
Revisons |  | User Needs FlowChart | EDS | CAD
MC |  | 15 min | 30 min
BC |  | 10 min | 30 min
VP
AH |  |  |  | 4 Hr
Signatures | Date | Date | Time | Date | Time
Brayden Chipman | 2024-01-21 | 2024-01-24 | 22:36 | 2024-03-08 | 18:16
Miguel Cruz | 2024-01-22 | 2024-01-24 | 22:36 | 2024-03-08 | 18:16
Vance Padilla | 2024-01-22 | 2024-01-24 | 22:45 | 2024-03-08 | 18:16
Ashwin Halepet | 2024-01-22 | 2024-01-24 | 22:36 | 2024-03-07 | 19:37

## Spring Quarter
Task | 3/31-4/6 | 4/7-4/13 | 4/14-4/20 | 4/21-4/27 | 4/28-5-4 | 5/5-5/11 | 5/12-5/18 | 5/19-5/25 | 5/26-6/1 | 6/2-6/8 | 6/9-6/13
Team Meeting | 30 min | 45 min | 20 min | 40 min | 1 hr | 1 hr | 1 hr | 1 hr | 1 hr | 1 hr
Client Meeting
Weekly Deliverables | Critical Path Analysis | n/a | Critical Path Analysis | n/a |  |  | Design Symposium Program Materials
MC | 1 hr |  | 5 min |  |  |  | 1 hr | 1 hr
BC | 30 min | [5 empty] | 30 min
VP | 30 min
AH | 30 min
Testing | Components | Components | Subsystems/Full Assembly
MC
BC
VP | 2 Hrs | 4 hrs | [7 empty] | 2 hrs
AH |  |  | 1 Hr | [6 empty] | 1 hr
Pair Tasks
MC-Circuit+Soldering |  | 3 Hrs |  | 1 Hr |  |  |  | 4 Hrs | 2 Hrs | 1 hr
BC-CAD | 1 Hr | 3 Hr | 2 Hr
VP-Circuit Assembly and Code | 2 Hrs | 2 Hrs |  | 2 Hrs
AH-CAD | 2 hrs | 6 Hrs |  | 6 Hrs |  |  |  | 4 Hr | 2 Hr | 1 Hr
Assembly | Circuit | Circuit | Full Assembly
MC |  | 2 Hrs |  | 2 Hrs |  |  |  |  | 3 hrs | 1 hr
BC |  |  |  | 1/2 Hr
VP | 2 Hrs | 3Hrs |  | 1Hr
AH |  |  |  | 2 Hrs |  |  |  |  | 4 Hr | 3 Hr
TA Meeting | 20 min | 30 min | 20 min | 40 min | 30 min | 30 min | 30 min | 20 min | 2.5 hrs | 30 min
Design Review | [5 empty] | Progress Report
MC |  |  | 30 min | 30 min |  | 30 min | 2 hrs | 1 hr | 4 hrs | 5 hrs
BC | [6 empty] | 1 hr | 1 hr | 4 hrs | 2 hrs
VP | [7 empty] | 1 Hr | 2Hr | 2Hrs
AH | [8 empty] | 2 Hr | 1 Hr
Revisons
MC | [9 empty] | 1 hr
BC | [9 empty] | 4 hr
VP | [9 empty] | 1 Hr
AH
Signatures
Brayden Chipman | 2024-04-22 20:36 | 2024-06-05 21:03
Miguel Cruz | 2024-04-22 21:45 | 2024-06-05 19:23
Vance Padilla | 2024-04-22 22:10 | 2024-06-05 14:06
Ashwin Halepet | 2024-04-22 22:01 | 2024-06-05 21:45